{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":185,"n_cols":15,"rows_kept":185,"merged":[[0,0,0,14]],"flags":["formulas_cached_only"]}
["IEEE 12207 Cost Model (Development Process)"]
["WBS#","WBS Task","Pages","Project Manager","System Analyst","System Architect","Software Analyst","Software Architect","Software Designer","Software Coder","Software Integrator","Software Tester","System Integrator","System Tester","Total"]
["1.0","IEEE 12207 Development Process",null,{"v":2835.4027777777774,"d":"2835"},{"v":612.7857142857142,"d":"613"},{"v":661.3095238095239,"d":"661"},{"v":1624.43253968254,"d":"1624"},{"v":3682.9087301587297,"d":"3683"},{"v":3755.646825396825,"d":"3756"},{"v":7085.123015873014,"d":"7085"},{"v":3292.646825396825,"d":"3293"},{"v":3177.3849206349205,"d":"3177"},{"v":1352.4325396825395,"d":"1352"},{"v":897.5714285714284,"d":"898"},{"v":28977.64484126984,"d":"28978"}]
[1.1,"System Requirements Analysis",null,{"v":70.38333333333334,"d":"70"},{"v":156.26190476190476,"d":"156"},{"v":68.26190476190476,"d":"68"},{"v":68.26190476190476,"d":"68"},{"v":33.26190476190476,"d":"33"},16,16,16,{"v":33.26190476190476,"d":"33"},{"v":68.26190476190476,"d":"68"},{"v":68.26190476190476,"d":"68"},{"v":614.2166666666667,"d":"614"}]
["1.1.1 ","SRS",50,8,80,0,0,0,0,0,0,0,0,0,88]
["1.1.2 ","System Requirements Evaluation",null,{"v":29.583333333333336,"d":"30"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":17.261904761904763,"d":"17"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":325.4166666666667,"d":"325"}]
["1.1.2.1 ","SRS Walkthroughs",null,{"v":12.083333333333334,"d":"12"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":132.91666666666666,"d":"133"}]
["1.1.2.2 ","SRS Inspections",null,{"v":17.5,"d":"18"},35,35,35,0,0,0,0,0,35,35,{"v":192.5,"d":"193"}]
["1.1.3 ","System Requirements Review",null,32,16,16,16,16,16,16,16,16,16,16,192]
["1.1.4 ","Functional Baseline",null,{"v":0.8,"d":"1"},8,0,0,0,0,0,0,0,0,0,{"v":8.8,"d":"9"}]
[1.2,"System Architectural Design",null,{"v":107.16666666666667,"d":"107"},16,{"v":280.5238095238095,"d":"281"},{"v":120.52380952380952,"d":"121"},{"v":120.52380952380952,"d":"121"},{"v":50.523809523809526,"d":"51"},16,{"v":50.523809523809526,"d":"51"},{"v":120.52380952380952,"d":"121"},{"v":120.52380952380952,"d":"121"},16,{"v":1018.8333333333334,"d":"1019"}]
["1.2.1 ","SARAD",100,16,0,160,0,0,0,0,0,0,0,0,176]
["1.2.2 ","System Architecture Evaluation",null,{"v":59.16666666666667,"d":"59"},0,{"v":104.52380952380952,"d":"105"},{"v":104.52380952380952,"d":"105"},{"v":104.52380952380952,"d":"105"},{"v":34.523809523809526,"d":"35"},0,{"v":34.523809523809526,"d":"35"},{"v":104.52380952380952,"d":"105"},{"v":104.52380952380952,"d":"105"},0,{"v":650.8333333333334,"d":"651"}]
["1.2.2.1 ","SARAD Walkthroughs",null,{"v":24.166666666666668,"d":"24"},0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.2.2.2 ","SARAD Inspections",null,35,0,70,70,70,0,0,0,70,70,0,385]
["1.2.3 ","System Design Review",null,32,16,16,16,16,16,16,16,16,16,16,192]
[1.3,"Software Requirements Analysis",null,{"v":145.55,"d":"146"},16,16,{"v":420.7857142857143,"d":"421"},{"v":172.78571428571428,"d":"173"},{"v":172.78571428571428,"d":"173"},{"v":67.78571428571428,"d":"68"},{"v":172.78571428571428,"d":"173"},{"v":172.78571428571428,"d":"173"},16,16,{"v":1389.2642857142855,"d":"1389"}]
["1.3.1 ","SRD",150,24,0,0,240,0,0,0,0,0,0,0,264]
["1.3.2 ","Software Requirements Evaluation",null,{"v":88.75,"d":"89"},0,0,{"v":156.78571428571428,"d":"157"},{"v":156.78571428571428,"d":"157"},{"v":156.78571428571428,"d":"157"},{"v":51.785714285714285,"d":"52"},{"v":156.78571428571428,"d":"157"},{"v":156.78571428571428,"d":"157"},0,0,{"v":924.4642857142858,"d":"924"}]
["1.3.2.1 ","SRD Walkthroughs",null,{"v":36.25,"d":"36"},0,{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},0,0,{"v":398.74999999999994,"d":"399"}]
["1.3.2.2 ","SRD Inspections",null,{"v":52.5,"d":"53"},0,0,105,105,105,0,105,105,0,0,{"v":577.5,"d":"578"}]
["1.3.3 ","Software Specification Review",null,32,16,16,16,16,16,16,16,16,16,16,192]
["1.3.4 ","Allocated Baseline",null,{"v":0.8,"d":"1"},0,0,8,0,0,0,0,0,0,0,{"v":8.8,"d":"9"}]
[1.4,"Software Architectural Design",null,{"v":390.25,"d":"390"},24,24,{"v":179.35714285714286,"d":"179"},{"v":1086.357142857143,"d":"1086"},{"v":494.3571428571429,"d":"494"},{"v":494.3571428571429,"d":"494"},{"v":662.3571428571429,"d":"662"},{"v":494.3571428571429,"d":"494"},{"v":179.35714285714286,"d":"179"},24,{"v":4052.7500000000005,"d":"4053"}]
["1.4.1 ","SAD",200,32,0,0,0,320,0,0,0,0,0,0,352]
["1.4.2 ","SIDD (Top-Level)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.4.3 ","DDD (Top-Level)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.4.4 ","UDD (Preliminary)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.4.5 ","TVPL (Software Integration)",100,16,0,0,0,0,0,0,160,0,0,0,176]
["1.4.6 ","Software Architecture Evaluation",null,{"v":266.25,"d":"266"},0,0,{"v":155.35714285714286,"d":"155"},{"v":470.3571428571429,"d":"470"},{"v":470.3571428571429,"d":"470"},{"v":470.3571428571429,"d":"470"},{"v":470.3571428571429,"d":"470"},{"v":470.3571428571429,"d":"470"},{"v":155.35714285714286,"d":"155"},0,{"v":2928.7500000000005,"d":"2929"}]
["1.4.6.1 ","Software Architecture Walkthroughs",null,{"v":108.75,"d":"109"},0,0,{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},{"v":155.35714285714286,"d":"155"},0,{"v":1196.2500000000002,"d":"1196"}]
["1.4.6.1.1 ","SAD",null,{"v":48.333333333333336,"d":"48"},0,0,{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},0,{"v":531.6666666666666,"d":"532"}]
["1.4.6.1.2 ","SIDD (Top-Level)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.4.6.1.3 ","DDD (Top-Level)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.4.6.1.4 ","UDD (Preliminary)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.4.6.1.5 ","TVPL (Software Integration)",null,{"v":24.166666666666668,"d":"24"},0,0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.4.6.2 ","Software Architecture Inspections",null,{"v":157.5,"d":"158"},0,0,0,315,315,315,315,315,0,0,{"v":1732.5,"d":"1733"}]
["1.4.6.2.1 ","SAD",null,70,0,0,0,140,140,140,140,140,0,0,770]
["1.4.6.2.2 ","SIDD (Top-Level)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.4.6.2.3 ","DDD (Top-Level)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.4.6.2.4 ","UDD (Preliminary)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.4.6.2.5 ","TVPL (Software Integration)",null,35,0,0,0,70,70,70,70,70,0,0,385]
["1.4.7 ","Preliminary Design Review",null,48,24,24,24,24,24,24,24,24,24,24,288]
["1.4.7.1 ","SAD",null,{"v":9.6,"d":"10"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":57.59999999999999,"d":"58"}]
["1.4.7.2 ","SIDD (Top-Level)",null,{"v":9.6,"d":"10"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":57.59999999999999,"d":"58"}]
["1.4.7.3 ","DDD (Top-Level)",null,{"v":9.6,"d":"10"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":57.59999999999999,"d":"58"}]
["1.4.7.4 ","UDD (Preliminary)",null,{"v":9.6,"d":"10"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":57.59999999999999,"d":"58"}]
["1.4.7.5 ","TVPL (Software Integration)",null,{"v":9.6,"d":"10"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":4.8,"d":"5"},{"v":57.59999999999999,"d":"58"}]
["1.4.8 ","Developmental Configuration",null,4,0,0,0,32,0,0,8,0,0,0,44]
[1.5,"Software Detailed Design",null,{"v":519.8,"d":"520"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":239.14285714285714,"d":"239"},{"v":747.1428571428571,"d":"747"},{"v":1491.142857142857,"d":"1491"},{"v":659.1428571428571,"d":"659"},{"v":747.1428571428571,"d":"747"},{"v":659.1428571428571,"d":"659"},{"v":239.14285714285714,"d":"239"},{"v":31.999999999999996,"d":"32"},{"v":5397.799999999999,"d":"5398"}]
["1.5.1 ","SDD",250,40,0,0,0,0,400,0,0,0,0,0,440]
["1.5.2 ","SIDD (Detailed)",100,16,0,0,0,0,160,0,0,0,0,0,176]
["1.5.3 ","DDD (Detailed)",100,16,0,0,0,0,160,0,0,0,0,0,176]
["1.5.4 ","UDD (Update)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.5.5 ","TVPL (Software Unit)",50,8,0,0,0,0,80,0,0,0,0,0,88]
["1.5.6 ","TVPL (Software Integration-Update)",50,8,0,0,0,0,0,0,80,0,0,0,88]
["1.5.7 ","Software Design Evaluation",null,355,0,0,{"v":207.14285714285714,"d":"207"},{"v":627.1428571428571,"d":"627"},{"v":627.1428571428571,"d":"627"},{"v":627.1428571428571,"d":"627"},{"v":627.1428571428571,"d":"627"},{"v":627.1428571428571,"d":"627"},{"v":207.14285714285714,"d":"207"},0,{"v":3904.9999999999995,"d":"3905"}]
["1.5.7.1 ","Software Design Walkthroughs",null,{"v":145.00000000000003,"d":"145"},0,0,{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},{"v":207.14285714285714,"d":"207"},0,1595]
["1.5.7.1.1 ","SDD",null,{"v":60.41666666666668,"d":"60"},0,0,{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},{"v":86.30952380952381,"d":"86"},0,{"v":664.5833333333334,"d":"665"}]
["1.5.7.1.2 ","SIDD (Detailed)",null,{"v":24.166666666666668,"d":"24"},0,0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.5.7.1.3 ","DDD (Detailed)",null,{"v":24.166666666666668,"d":"24"},0,0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.5.7.1.4 ","UDD (Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.5.7.1.5 ","TVPL (Software Unit)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.5.7.1.6 ","TVPL (Software Integration-Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.5.7.2 ","Software Design Inspections",null,210,0,0,0,420,420,420,420,420,0,0,2310]
["1.5.7.2.1 ","SDD ",null,{"v":87.5,"d":"88"},0,0,0,175,175,175,175,175,0,0,{"v":962.5,"d":"963"}]
["1.5.7.2.2 ","SIDD (Detailed)",null,35,0,0,0,70,70,70,70,70,0,0,385]
["1.5.7.2.3 ","DDD (Detailed)",null,35,0,0,0,70,70,70,70,70,0,0,385]
["1.5.7.2.4 ","UDD (Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.5.7.2.5 ","TVPL (Software Unit)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.5.7.2.6 ","TVPL (Software Integration-Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.5.8 ","Critical Design Review",null,{"v":64.00000000000001,"d":"64"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},{"v":31.999999999999996,"d":"32"},384]
["1.5.8.1 ","SDD",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.8.2 ","SIDD (Detailed)",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.8.3 ","DDD (Detailed)",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.8.4 ","UDD (Update)",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.8.5 ","TVPL (Software Unit)",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.8.6 ","TVPL (Software Integration-Update)",null,{"v":10.666666666666668,"d":"11"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},64]
["1.5.9 ","Developmental Configuration",null,{"v":4.800000000000001,"d":"5"},0,0,0,8,32,0,8,0,0,0,{"v":52.8,"d":"53"}]
[1.6,"Software Coding and Testing",null,{"v":759.3194444444443,"d":"759"},0,0,{"v":152.4801587301587,"d":"152"},{"v":549.6468253968253,"d":"550"},{"v":765.6468253968253,"d":"766"},{"v":4961.646825396825,"d":"4962"},{"v":549.6468253968253,"d":"550"},{"v":461.6468253968253,"d":"462"},{"v":152.4801587301587,"d":"152"},0,{"v":8352.513888888889,"d":"8353"}]
["1.6.1 ","Software Development",null,416,0,0,0,0,160,4000,0,0,0,0,4576]
["1.6.1.1 ","Software Unit and Database",{"v":166.66666666666666,"d":"167"},400,0,0,0,0,0,4000,0,0,0,0,4400]
["1.6.1.2 ","TVPR (Software Unit and Database)",100,16,0,0,0,0,160,0,0,0,0,0,176]
["1.6.2 ","TVRR (Unit and Database)",75,12,0,0,0,0,120,0,0,0,0,0,132]
["1.6.3 ","UDD (Software Update)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.6.4 ","TVPL (Software Integration-Update)",50,8,0,0,0,0,0,0,80,0,0,0,88]
["1.6.5 ","Software Coding and Testing Evaluation",null,{"v":261.3194444444444,"d":"261"},0,0,{"v":152.4801587301587,"d":"152"},{"v":461.6468253968253,"d":"462"},{"v":461.6468253968253,"d":"462"},{"v":461.6468253968253,"d":"462"},{"v":461.6468253968253,"d":"462"},{"v":461.6468253968253,"d":"462"},{"v":152.4801587301587,"d":"152"},0,{"v":2874.5138888888882,"d":"2875"}]
["1.6.5.1 ","Software Coding and Testing Walkthroughs",null,{"v":106.7361111111111,"d":"107"},0,0,{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},{"v":152.4801587301587,"d":"152"},0,{"v":1174.097222222222,"d":"1174"}]
["1.6.5.1.1 ","Software Unit and Database",null,{"v":40.27777777777777,"d":"40"},0,0,{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},{"v":57.53968253968253,"d":"58"},0,{"v":443.0555555555555,"d":"443"}]
["1.6.5.1.2 ","TVPR (Software Unit and Database)",null,{"v":24.166666666666668,"d":"24"},0,0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.6.5.1.3 ","TVRR (Software Unit and Database)",null,{"v":18.125,"d":"18"},0,0,{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},{"v":25.892857142857142,"d":"26"},0,{"v":199.37499999999997,"d":"199"}]
["1.6.5.1.4 ","UDD (Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.6.5.1.5 ","TVPL (Software Integration-Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.6.5.2 ","Software Coding and Testing Inspections",null,{"v":154.58333333333331,"d":"155"},0,0,0,{"v":309.16666666666663,"d":"309"},{"v":309.16666666666663,"d":"309"},{"v":309.16666666666663,"d":"309"},{"v":309.16666666666663,"d":"309"},{"v":309.16666666666663,"d":"309"},0,0,{"v":1700.416666666666,"d":"1700"}]
["1.6.5.2.1 ","Software Unit and Database",null,{"v":58.33333333333333,"d":"58"},0,0,0,{"v":116.66666666666666,"d":"117"},{"v":116.66666666666666,"d":"117"},{"v":116.66666666666666,"d":"117"},{"v":116.66666666666666,"d":"117"},{"v":116.66666666666666,"d":"117"},0,0,{"v":641.6666666666665,"d":"642"}]
["1.6.5.2.2 ","TVPR (Software Unit and Database)",null,35,0,0,0,70,70,70,70,70,0,0,385]
["1.6.5.2.3 ","TVRR (Software Unit and Database)",null,{"v":26.25,"d":"26"},0,0,0,{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},0,0,{"v":288.75,"d":"289"}]
["1.6.5.2.4 ","UDD (Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.6.5.2.5 ","TVPL (Software Integration-Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.6.6 ","Developmental Configuration",null,54,0,0,0,8,24,500,8,0,0,0,594]
[1.7,"Software Integration",null,{"v":333.875,"d":"334"},24,24,{"v":153.46428571428572,"d":"153"},{"v":503.9642857142857,"d":"504"},{"v":415.9642857142857,"d":"416"},{"v":415.9642857142857,"d":"416"},{"v":639.9642857142858,"d":"640"},{"v":743.9642857142858,"d":"744"},{"v":153.46428571428572,"d":"153"},24,{"v":3432.6250000000005,"d":"3433"}]
["1.7.1 ","SOIP",100,16,0,0,0,0,0,0,160,0,0,0,176]
["1.7.2 ","TVRR (Software Integration)",25,4,0,0,0,0,0,0,40,0,0,0,44]
["1.7.3 ","UDD (Update)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.7.4 ","TVPR (Software Qualification)",200,32,0,0,0,0,0,0,0,320,0,0,352]
["1.7.5 ","Software Integration Evaluation",null,{"v":221.875,"d":"222"},0,0,{"v":129.46428571428572,"d":"129"},{"v":391.9642857142857,"d":"392"},{"v":391.9642857142857,"d":"392"},{"v":391.9642857142857,"d":"392"},{"v":391.9642857142857,"d":"392"},{"v":391.9642857142857,"d":"392"},{"v":129.46428571428572,"d":"129"},0,{"v":2440.625,"d":"2441"}]
["1.7.5.1 ","Software Integration Walkthroughs",null,{"v":90.625,"d":"91"},0,0,{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},{"v":129.46428571428572,"d":"129"},0,{"v":996.8750000000002,"d":"997"}]
["1.7.5.1.1 ","SOIP",null,{"v":24.166666666666668,"d":"24"},0,0,{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},0,{"v":265.8333333333333,"d":"266"}]
["1.7.5.1.2 ","TVRR (Software Integration)",null,{"v":6.041666666666667,"d":"6"},0,0,{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},0,{"v":66.45833333333333,"d":"66"}]
["1.7.5.1.3 ","UDD (Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.7.5.1.4 ","TVPR (Software Qualification)",null,{"v":48.333333333333336,"d":"48"},0,0,{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},{"v":69.04761904761905,"d":"69"},0,{"v":531.6666666666666,"d":"532"}]
["1.7.5.2 ","Software Integration Inspections",null,{"v":131.25,"d":"131"},0,0,0,{"v":262.5,"d":"263"},{"v":262.5,"d":"263"},{"v":262.5,"d":"263"},{"v":262.5,"d":"263"},{"v":262.5,"d":"263"},0,0,{"v":1443.75,"d":"1444"}]
["1.7.5.2.1 ","SOIP",null,35,0,0,0,70,70,70,70,70,0,0,385]
["1.7.5.2.2 ","TVRR (Software Integration)",null,{"v":8.75,"d":"9"},0,0,0,{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},0,0,{"v":96.25,"d":"96"}]
["1.7.5.2.3 ","UDD (Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.7.5.2.4 ","TVPR (Software Qualification)",null,70,0,0,0,140,140,140,140,140,0,0,770]
["1.7.6 ","Software Test Readiness Review",null,48,24,24,24,24,24,24,24,24,24,24,288]
["1.7.6.1 ","SOIP",null,12,6,6,6,6,6,6,6,6,6,6,72]
["1.7.6.2 ","TVRR (Software Integration)",null,12,6,6,6,6,6,6,6,6,6,6,72]
["1.7.6.3 ","UDD (Update)",null,12,6,6,6,6,6,6,6,6,6,6,72]
["1.7.6.4 ","TVPR (Software Qualification)",null,12,6,6,6,6,6,6,6,6,6,6,72]
["1.7.7 ","Test Baseline (Software Integration)",null,4,0,0,0,8,0,0,24,8,0,0,44]
[1.8,"Software Qualification Testing",null,{"v":159.575,"d":"160"},48,48,{"v":73.89285714285714,"d":"74"},{"v":246.39285714285714,"d":"246"},{"v":126.39285714285714,"d":"126"},{"v":126.39285714285714,"d":"126"},{"v":126.39285714285714,"d":"126"},{"v":198.39285714285714,"d":"198"},{"v":73.89285714285714,"d":"74"},48,{"v":1275.3249999999998,"d":"1275"}]
["1.8.1 ","TVRR (Software Qualification)",25,4,0,0,0,0,0,0,0,40,0,0,44]
["1.8.2 ","UDD (Update)",50,8,0,0,0,80,0,0,0,0,0,0,88]
["1.8.3 ","Software Qualification Evaluation",null,{"v":44.375,"d":"44"},0,0,{"v":25.892857142857146,"d":"26"},{"v":78.39285714285714,"d":"78"},{"v":78.39285714285714,"d":"78"},{"v":78.39285714285714,"d":"78"},{"v":78.39285714285714,"d":"78"},{"v":78.39285714285714,"d":"78"},{"v":25.892857142857146,"d":"26"},0,{"v":488.12499999999994,"d":"488"}]
["1.8.3.1 ","Software Qualification Walkthroughs",null,{"v":18.125,"d":"18"},0,0,{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},{"v":25.892857142857146,"d":"26"},0,{"v":199.375,"d":"199"}]
["1.8.3.1.1 ","TVRR (Software Qualification)",null,{"v":6.041666666666667,"d":"6"},0,0,{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},0,{"v":66.45833333333333,"d":"66"}]
["1.8.3.1.2 ","UDD (Update)",null,{"v":12.083333333333334,"d":"12"},0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,{"v":132.91666666666666,"d":"133"}]
["1.8.3.2 ","Software Qualification Inspections",null,{"v":26.25,"d":"26"},0,0,0,{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},{"v":52.5,"d":"53"},0,0,{"v":288.75,"d":"289"}]
["1.8.3.2.1 ","TVRR (Software Qualification)",null,{"v":8.75,"d":"9"},0,0,0,{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},0,0,{"v":96.25,"d":"96"}]
["1.8.3.2.2 ","UDD (Update)",null,{"v":17.5,"d":"18"},0,0,0,35,35,35,35,35,0,0,{"v":192.5,"d":"193"}]
["1.8.4 ","SIAR (Software FCA and PCA) Development",null,{"v":3.2,"d":"3"},0,0,0,32,0,0,0,0,0,0,{"v":35.2,"d":"35"}]
["1.8.4.1 ","SIAR (Software FCA)",null,{"v":1.6,"d":"2"},0,0,0,16,0,0,0,0,0,0,{"v":17.6,"d":"18"}]
["1.8.4.2 ","SIAR (Software PCA)",null,{"v":1.6,"d":"2"},0,0,0,16,0,0,0,0,0,0,{"v":17.6,"d":"18"}]
["1.8.5 ","Software Formal Qualification Review",null,96,48,48,48,48,48,48,48,48,48,48,576]
["1.8.5.1 ","TVRR (Qualification)",null,24,12,12,12,12,12,12,12,12,12,12,144]
["1.8.5.2 ","UDD (Update)",null,24,12,12,12,12,12,12,12,12,12,12,144]
["1.8.5.3 ","SIAR (Software FCA)",null,24,12,12,12,12,12,12,12,12,12,12,144]
["1.8.5.4 ","SIAR (Software PCA)",null,24,12,12,12,12,12,12,12,12,12,12,144]
["1.8.6 ","Software Product Baseline",null,4,0,0,0,8,0,0,0,32,0,0,44]
[1.9,"System Integration",null,{"v":165.94166666666666,"d":"166"},16,16,16,{"v":76.41666666666666,"d":"76"},{"v":76.41666666666666,"d":"76"},{"v":198.91666666666666,"d":"199"},{"v":198.91666666666666,"d":"199"},{"v":198.91666666666666,"d":"199"},{"v":254.91666666666666,"d":"255"},{"v":446.91666666666663,"d":"447"},{"v":1665.3583333333331,"d":"1665"}]
["1.9.1 ","TVRR (System Integration)",25,4,0,0,0,0,0,0,0,0,40,0,44]
["1.9.2 ","TVPR (System Qualification)",150,24,0,0,0,0,0,0,0,0,0,240,264]
["1.9.3 ","System Integration Evaluation",null,{"v":103.54166666666666,"d":"104"},0,0,0,{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":182.91666666666666,"d":"183"},{"v":182.91666666666666,"d":"183"},{"v":182.91666666666666,"d":"183"},{"v":182.91666666666666,"d":"183"},{"v":182.91666666666666,"d":"183"},{"v":1138.9583333333333,"d":"1139"}]
["1.9.3.1 ","System Integration Walkthroughs",null,{"v":42.291666666666664,"d":"42"},0,0,0,{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":60.416666666666664,"d":"60"},{"v":465.20833333333337,"d":"465"}]
["1.9.3.1.1 ","TVRR (System Integration)",null,{"v":6.041666666666667,"d":"6"},0,0,0,{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":66.45833333333333,"d":"66"}]
["1.9.3.1.2 ","TVPR (System Qualification)",null,{"v":36.25,"d":"36"},0,0,0,{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":51.785714285714285,"d":"52"},{"v":398.74999999999994,"d":"399"}]
["1.9.3.2 ","System Integration Inspections",null,{"v":61.25,"d":"61"},0,0,0,0,0,{"v":122.5,"d":"123"},{"v":122.5,"d":"123"},{"v":122.5,"d":"123"},{"v":122.5,"d":"123"},{"v":122.5,"d":"123"},{"v":673.75,"d":"674"}]
["1.9.3.2.1 ","TVRR (System Integration)",null,{"v":8.75,"d":"9"},0,0,0,0,0,{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":96.25,"d":"96"}]
["1.9.3.2.2 ","TVPR (System Qualification)",null,{"v":52.5,"d":"53"},0,0,0,0,0,105,105,105,105,105,{"v":577.5,"d":"578"}]
["1.9.4 ","System Test Readiness Review",null,32,16,16,16,16,16,16,16,16,16,16,192]
["1.9.4.1 ","TVRR (System Integration) Review",null,16,8,8,8,8,8,8,8,8,8,8,96]
["1.9.4.2 ","TVPR (System Qualification) Review",null,16,8,8,8,8,8,8,8,8,8,8,96]
["1.9.5 ","Test Baseline (System Integration)",null,{"v":2.4000000000000004,"d":"2"},0,0,0,0,0,0,0,0,16,8,{"v":26.4,"d":"26"}]
["1.10","System Qualification Testing",null,{"v":62.791666666666664,"d":"63"},16,48,16,{"v":24.63095238095238,"d":"25"},{"v":24.63095238095238,"d":"25"},{"v":42.13095238095238,"d":"42"},{"v":42.13095238095238,"d":"42"},{"v":42.13095238095238,"d":"42"},{"v":42.13095238095238,"d":"42"},{"v":90.13095238095238,"d":"90"},{"v":450.70833333333337,"d":"451"}]
["1.10.1 ","TVRR (System Qualification)",25,4,0,0,0,0,0,0,0,0,0,40,44]
["1.10.2 ","System Qualification Evaluation",null,{"v":14.791666666666668,"d":"15"},0,0,0,{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":26.13095238095238,"d":"26"},{"v":26.13095238095238,"d":"26"},{"v":26.13095238095238,"d":"26"},{"v":26.13095238095238,"d":"26"},{"v":26.13095238095238,"d":"26"},{"v":162.70833333333334,"d":"163"}]
["1.10.2.1 ","TVRR (System Qualification) Walkthroughs",null,{"v":6.041666666666667,"d":"6"},0,0,0,{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":8.630952380952381,"d":"9"},{"v":66.45833333333333,"d":"66"}]
["1.10.2.2 ","TVRR (System Qualification) Inspections",null,{"v":8.75,"d":"9"},0,0,0,0,0,{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":17.5,"d":"18"},{"v":96.25,"d":"96"}]
["1.10.3 ","SIAR (System FCA and PCA) Development",null,{"v":3.2,"d":"3"},0,32,0,0,0,0,0,0,0,0,{"v":35.2,"d":"35"}]
["1.10.3.1 ","SIAR (System FCA)",null,{"v":1.6,"d":"2"},0,16,0,0,0,0,0,0,0,0,{"v":17.6,"d":"18"}]
["1.10.3.2 ","SIAR (System PCA)",null,{"v":1.6,"d":"2"},0,16,0,0,0,0,0,0,0,0,{"v":17.6,"d":"18"}]
["1.10.4 ","System Formal Qualification Review",null,40,16,16,16,16,16,16,16,16,16,16,200]
["1.10.4.1 ","TVRR (System Qualification)",null,{"v":13.333333333333334,"d":"13"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":66.66666666666667,"d":"67"}]
["1.10.4.2 ","SIAR (System FCA)",null,{"v":13.333333333333334,"d":"13"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":66.66666666666667,"d":"67"}]
["1.10.4.3 ","SIAR (System PCA)",null,{"v":13.333333333333334,"d":"13"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":5.333333333333333,"d":"5"},{"v":66.66666666666667,"d":"67"}]
["1.10.5 ","System Product Baseline",null,{"v":0.8,"d":"1"},0,0,0,0,0,0,0,0,0,8,{"v":8.8,"d":"9"}]
[1.11,"Software Installation",null,{"v":41.583333333333336,"d":"42"},{"v":92.26190476190476,"d":"92"},{"v":52.26190476190476,"d":"52"},{"v":132.26190476190476,"d":"132"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":457.41666666666663,"d":"457"}]
["1.11.1 ","SIP",50,8,0,0,80,0,0,0,0,0,0,0,88]
["1.11.2 ","Software Installation Evaluation",null,{"v":29.583333333333336,"d":"30"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":325.41666666666663,"d":"325"}]
["1.11.2.1 ","SIP Walkthroughs",null,{"v":12.083333333333334,"d":"12"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":132.91666666666666,"d":"133"}]
["1.11.2.2 ","SIP Inspections",null,{"v":17.5,"d":"18"},35,35,35,35,35,0,0,0,0,0,{"v":192.5,"d":"193"}]
["1.11.3 ","Software Installation",null,4,40,0,0,0,0,0,0,0,0,0,44]
[1.12,"Software Acceptance Support",null,{"v":79.16666666666667,"d":"79"},{"v":172.26190476190476,"d":"172"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":132.26190476190476,"d":"132"},{"v":870.8333333333335,"d":"871"}]
["1.12.1 ","TVRR (Software Acceptance)",50,8,0,0,0,0,0,0,0,0,0,80,88]
["1.12.2 ","Software Training",50,8,80,0,0,0,0,0,0,0,0,0,88]
["1.12.3 ","Software Acceptance Evaluation",null,{"v":59.16666666666667,"d":"59"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":69.52380952380952,"d":"70"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":52.26190476190476,"d":"52"},{"v":650.8333333333335,"d":"651"}]
["1.12.3.1 ","Software Acceptance Walkthroughs",null,{"v":24.166666666666668,"d":"24"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":34.523809523809526,"d":"35"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":265.8333333333333,"d":"266"}]
["1.12.3.1.1 ","TVRR (Software Acceptance)",null,{"v":12.083333333333334,"d":"12"},0,0,0,{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":132.91666666666666,"d":"133"}]
["1.12.3.1.2 ","Software Training",null,{"v":12.083333333333334,"d":"12"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},{"v":17.261904761904763,"d":"17"},0,0,0,{"v":132.91666666666666,"d":"133"}]
["1.12.3.2 ","Software Acceptance Inspections",null,35,35,35,35,35,35,35,35,35,35,35,385]
["1.12.3.2.1 ","TVRR (Software Acceptance)",null,{"v":17.5,"d":"18"},0,0,0,0,0,35,35,35,35,35,{"v":192.5,"d":"193"}]
["1.12.3.2.2 ","Software Training",null,{"v":17.5,"d":"18"},35,35,35,35,35,0,0,0,0,0,{"v":192.5,"d":"193"}]
["1.12.4 ","Software Delivery",null,4,40,0,0,0,0,0,0,0,0,0,44]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}